## Slide 1: BCBS Testing Strategy

## Slide 2
PDM
SA -
SVC_TEST_CACTUS_MINN
DB -CACTUS_MIN1
Has Uma updated the Matillion IIT repository with the service account.
For new account , create the ID in vault and provide the secret name. Uma can find it.
Same repository with different env variable.
Mahi coordinate with Uma.

## Slide 3
Testing Strategy
Identify app to be tested
Validate data Stage runbook availability
Identify source & target table/file
Verify Matillion job access to jobs
Prepare test plan
Prepare test cases
Review test cases
A/B Test framework
Data sync data stage
Data sync matillion
Execute A/B Test
Raise bugs
Validate test result
Close defects in ADO
Test Summary result
Review & Approval
Prep
Plan
Execute
Report

## Slide 4
Execution Strategy – A/B Testing
A  Represent data from Data Stage & Netezza loaded into Unix server.
B  Represent data from Matillion & Snowflake loaded into Azure blob
A/B Testing framework covers below.
  Record count match
  Data set matches
  Data level validation
Manual Testing
  File Type match
  File name match
  File size match
  File Header match
  Job run in DS & Matillion
Demand A/B Testing – File based

## Slide 5
Execution Strategy – A/B Testing
MSS Supply A/B Testing – Table based
MSS Supply A/B Testing
A  Represent data from Data Stage & Netezza loaded into SQL database.
B  Represent data from Matillion & Snowflake loaded into SQL database.
A/B Testing framework covers this.
  Record count match
  Data set matches
  Data level validation
  Column validation

## Slide 6
 |  | total app | Completed | Work Remaining | Effort Hrs per app | no resources | Total effort hrs | Days Required | Planned Start | Planned End | Actual No of days | Resource Hrs
IIT |  |  |  |  |  |  |  |  |  |  |  | 
 | Demand Test |  |  |  |  |  |  |  |  |  |  | 
 | P1G2/P1G3/P1G4 | 27 | 8 | 19 | 32 | 3 | 608 | 25 | 25-Mar | 3-May | 30 | 
 | MSS Supply | 1 | 0 | 1 | 160 | 1.2 | 160 | 17 | 1-Apr | 26-Apr | 20 | 
 | MSS Demand | 1 | 0 | 1 | 60 | 1 | 60 | 8 | 29-Apr | 10-May | 10 | 
 | Bug Fixes |  |  |  |  | 6 | 1920 | - | 25-Mar | 10-May | 35 | 
 |  |  |  |  |  | . | 2748 |  |  |  | IIT Total | 
SIT |  |  |  |  |  |  |  |  |  |  |  | 
 | SIT Prep |  |  |  |  | 0.2 |  |  | 25-Mar | 10-May | 35 | 
 | P1G21/P1G3/P1G4 | 27 | 0 | 27 | 22 | 4 | 594 | 19 | 6-May | 7-Jun | 25 | 
 | MSS Supply | 1 | 0 | 1 | 80 | 1 | 80 | 10 | 3-Jun | 21-Jun | 15 | 
 | MSS Demand | 1 | 0 | 1 | 40 | 1 | 40 | 5 | 10-Jun | 21-Jun | 10 | 
 | Bug Fixes |  |  |  |  | 6 | 1920 | - | 6-May | 21-Jun | 35 | 
Test Execution Timeline

## Slide 7
Test Result Summary
AB Test Summary |  |  |  |  |  |  |  | 
Created By: Srinivasulu Naidu |  |  |  |  |  |  |  | 
Date | Count Check |  |  |  | Data Check |  |  | 
2024-03-18T03:43:34.34-04:00 | Count A | Count B | Expected Result | Result | A Minus B | B Minus A | Expected Result | Result
Tester: Srinivasulu Naidu | 356327 | 356327 | 100% match | Pass | 0 | 0 | Zero Record count for A-B and B-A | Pass
A/B framework Test result
 | Database / Server | File / Table
A |  | 
Test Minor Netezza Source | FDAMINOR.FDA, EDRMINOR.EDR | 
Test Minor DataStage | Unix Server | /data/uat/dmd1/HCBB/Lab_Data/output/ LAB_M01_LANDMARK_O_MTHLY_LABMEM_DATA_20240304_041420_01.TXT
Data Stage Job Execution Date | 03/04/2024 | 
Snowflake Source Database | FDADEVIIT_MIGRATION, EDRDEVIIT_MIGRATION | 
Snowflake Clone Date | 02/29/2024 10:43 AM ET | 
B |  | 
Matillion Source | FDADEVIIT_MIGRATION.FDA | 
Matillion Target | ADLS | datahub / demand / publish / HCBB / LAB_DATA/ LAB_D01_LANDMARK_O_MTHLY_LABMEM_DATA_20240304_041420_01.txt
Matillion Job Execution Date | 03/04/2024 | 
A/B framework setup