## Test Plan
Environment Name | IIT |  |  | Test Design OCL
App Name | OCL
App Type | Demand
Created By | Utpal Nayak
Creation Date | 2024-03-26
Reviewed By | Allen Mathew
Reviewed Date | 2024-03-27
Input table / Output File for Data Stage | A
| Database.Schema | Table Name
Input Table | FDATST6 | CMC_CLHC_COND_CODE CMC_CLCL_CLAIM CMC_CLCC_CARC_CODE FACILITY_FACT CMC_CDIO_L_ITS_OPL
| FACTST2 | VW_MEMBER VW_MEMBER_ELIGIBILITY_FACT VW_CLIENT_CONTRACT_DETAIL VW_PRODUCT_CLIENT_CONTRACT PRODUCT
| Unix Server | Location
Output File | britpuisapp74 | /data/prd/dmd/OCL/OCL_RECOVERY
Input table / File for Matillion | B
| Database.Schema | Table Name
Input tables | FDADEVIIT_MIGRATION.FDA | LAB_DATA_FACT, PROCEDURES, LAB_CODE_REF, MEMBER, MEMBER_ELIGIBILITY_FACT, CLIENT_CONTRACT_DETAIL, MARKET_SEGMENT, COMMON_PRACTITIONER
Output Tables/Files Location B | ADLS | datahub/demand/publish/HCBB / LAB_DATA
Output File Name | LAB_M01_LANDMARK_O_MTHLY_LABMEM_DATA_********.txt
Enviornments/Databases Required | Snowflake | DEVIIT_MIGRATION
| Netezza | TestMinor (FDATST6)
| SQL | Nil
| Oracle | Nil
Additional Access Required: | Unix UAT folder
Developer Contact for defects | Shekhar
Testing Activities:
AB Test Prep: | Update the AB Testing Config tables
Run: 1
Activity ID | Activity | Date | Day of week | AM/PM | Dependency | Responsibility
1 | Raise Ticket for DataStage Execution for next day with conformation that EDR/FDA flow has compelted |  | Friday | PM | 0 | Shiva, Testing Team,DC Team
2 | Confirm that DataStage process executed Successfully at expected time and created non empty file as expected |  | Monday | AM | 0 | Shiva, Testing Team,DC Team
3 | Raise SR request for cloning Snowflake TestMinor into DevIIT |  | Monday | AM | 0 | Testing Team
4 | Clone Testminor into DEV_IIT After SRDM completes |  | Monday | PM | 2 | Manoj,Ryo, Testing Team |  | DatStage
6 | Check if counts of required table's match between DevIIT and Testminor (optional) |  | Monday | PM | 0 | Testing Team, Amulya |  | 100
6 | Execute Matillion Job using DEV_IIT environment to create yesterday file (goal is not to compare outputs in cycle/Run 1 |  | Tuesday | AM | 4 | Chanchal(dev),Testing Team |  | 250
7 | Compare/(A)(B) Test the 2 output files generated by datastage and Matillion Process (If Full load Files)
Run: 2 | After Yesterday files generated from run 1 | [5 empty] | Daily
Activity ID | Activity | Date | Day of week | AM/PM | Dependency | Responsibility
1 | Raise Ticket for DataStage Execution for next day with conformation that EDR/FDA flow has compelted |  | Tuesday | PM | 0 | Shiva, Testing Team,DC Team
2 | Confirm that DataStage process executed Successfully at expected time and created non empty file as expected |  | Wednesday | AM | 0 | Shiva, Testing Team,DC Team
3 | Raise SR request for cloning Snowflake TestMinor into DevIIT after SRDM Compeltion |  | Wednesday | AM | 0 | Testing Team
4 | Clone Testminor into DEV_IIT After SRDM completes |  | Wednesday | PM | 2 | Manoj,Ryo, Testing Team |  | DatStage
6 | Check if counts of required table's match between DevIIT and Testminor (optional) |  | Wednesday | PM | 0 | Testing Team, Amulya |  | 100
6 | Execute Matillion Job using DEV_IIT environment to create yesterday file (goal is not to compare outputs in cycle/Run 1 |  | Thursday | AM | 4 | Chanchal(dev),Testing Team |  | 250
14 | Compare/(A)(B) Test the 2 output files generated by datastage and Matillion Process |  | Friday | AM,PM | Steps 1 to 13 | Testing Team
15 | Raise Defects in ADO |  | Friday | AM | Steps 1 to 14 | Testing Team
Negative Test Cases | (optional)
Folder not present
No Input data /Tables

## Test Cases
Environment Name | IIT
App Name | HCBB Labdata
App Type | Demand
Created By | Srinivasulu Naidu
Creation Date | 2024-02-19
Reviewed By | Chanchal Verma
Reviewed Date | 2024-02-24
Subject | Test Case ID | Test Case Description | Steps | Description [Design Description] | Expected Result | Actual Result | Status | Executed By | Executed Date | Test Type
| TC_001_HCBB_LabData | Source Input File - HCBB Demand App Run books should be run to create Source Input file | Step1 | Provider below RUNbook forHCBB providers by logging SNOW Ticket Run books Folder/Path : https://bcbsri.sharepoint.com/sites/CloudNativeDataProject-365copy-365/Shared%20Documents/Track%201%20-%20Datastage%20Netezza%20Migration/Demand/P1-G1/CDH%20Provider/Implementation%20Plan%20and%20Runbooks?csf=1&web=1&e=OA6xGf HWA - Repos (azure.com) | Job Completed sucessfully and Files are generated path - /data/uat/dmd1/HCBB/Lab_Data/output in the format LANDMARK_O_MTHLY_LABMEM_DATA.txt | Job completed successfully and confirmed by Rejija Purshotaman on 2024/02/26 | Pass | HWA Team,Allen | 2024/02/26 | Manual
| TC_002 HCBB_LabData | DataStage Output File Validation - Validate the files produced by the DataStage Process | Step1 | Log into Unix Server BRITPUISAPP74 and check if the file is present in the location /data/uat/dmd1/HCBB/Lab_Data/output in the format LAB_M01_LANDMARK_O_MTHLY_LABMEM_DATA.txt | The Source File should contain below table data: LAB_DATA_FACT, PROCEDURES, LAB_CODE_REF, MEMBER, MEMBER_ELIGIBILITY_FACT, CLIENT_CONTRACT_DETAIL, MARKET_SEGMENT, COMMON_PRACTITIONER | Job completed Successfully and file created by the name LAB_M01_LANDMARK_O_MTHLY_LABMEM_DATA in path path - /data/uat/dmd1/HCBB/Lab_Data/output in the format | Pass | HWA Team,Allen | 2024/02/26 | Manual
|  |  | Step 2 | Copy the file into Azure Data Lake datahub/demand/publish/CDH-London-health/provider/ and rename with _ds suffix | The file saved sucessfully | File copied successfully and saved as CDH_PROV_Daily_20240226_ds.mbi | Pass | Srinivas | 2024/02/27 | Manual
| TC_003_HCBB_LabData | Copy paste the above source file in ADLS | Step 1 | Log into ADLS and check if the file is present in datahub/demand/publish/HCBB / LAB_DATA File name - LAB_M01_LANDMARK_O_MTHLY_LABMEM_DATA_********.txt | File saved in the location | File Saved in the location | Pass | Srinivas | 2024/02/27 | Manual
| TC_004 CDH_ HCCBLabData | Run Matillion Job manually | Step 1 | Log into Matillion Link and follow Steps: 1.EDR Supply 2.Project Manage Version 3.DS_to_ MAT _Migration 4.Foundation Component 5. ABC 6.Testing Folder 7.O_AB testing Right Clink and select Run (Development migration) | Job will completes sucessfully Create target file in Matillion | Job Executed Successfully and results were saved in the location datahub/demand/publish/HCBB / LAB_DATA under the file name LAB_M01_LANDMARK_O_MTHLY_LABMEM_DATA_********.txt | Pass | Srinivas | 2024/02/28 | Manual
| TC_005 _ AB testing Framework comparing Source and target File in Snowflake | Validate Comparision file in SNOWFLAKE | Step1 | Validate number of tables in control table by executing below query: SQL 1 : SELECT * FROM LANDINGDEV_MIGRATION.SHARED_SCHEMA.TEST_CONTROL_TABLE; | Total table should be matched |  |  |  |  | Manual
|  |  | Step 2 | Validate summary in control table by executing below query: SQL 2 : SELECT top 3 * FROM LANDINGDEV_MIGRATION.SHARED_SCHEMA.AB_TEST_SUMMARY order by 1 desc; | Summary should be matched |  |  |  |  | Manual
|  |  | Step 3 | SELECT * FROM LANDINGDEV_MIGRATION.SHARED_SCHEMA.AB_TEST_ROW_REJECT_DETAIL where test_run_id=272; | If any data descripencies will be detailed here |  |  |  |  | Manual
| TC_006_ Validate number of Headers/Columns in File | Validate Header/Columns in File | Step1 | Validate number of Headers or columns in File 1. No. of Columns 2. No of Columns Name 3. No Space or Special characters in headers or columns | Headers or Columns should be matched exactly
| TC_007_ Validate number of rows and its values in File | Validate number of rows and its values in File | Step1 | Validate number of rows and its values in File 1. No. of Rows 2. No of Rows value or data 3. No Space or Special characters in rows | Number of Rows and its values should be matached
| TC_008_ Validate Data aligment and Format | Validate Data aligment and Format | Step 1 | Validate File data as below: 1. Data Aligment 2. Data format 3. Date format ( compare source file with target file) 4. Time stamp format( compare source file with target file) | Source File data and Target file data should be matched with the alignment, formate, date formate, date stamp.

## Data Synchronizatoin Timeline (hidden)
IST | 12:30 | 14:30 | 16:30 | 18:30 | 20:30 | 22:30 | 24:30 | 26:30 | 28:30 | 30:30 | 32:30 | 34:30 | 12:30
EST | 2:00 | 4:00 | 6:00 | 8:00 | 10:00 | 12:00 | 14:00 | 16:00 | 18:00 | 20:00 | 22:00 | 24:00 | 0:00
Monday
Matillion Compelte
Tuesday |  |  | Netezza TestMinor Refresh |  |  | Gap |  | SRDM REFRESH
Wednesday | SRDM REFRESH | [7 empty] | DEV IIT CLONING |  |  |  | Matillion Start (Thursday)
[6 empty] | DataStage SR Request |  |  | DataStage RUN
Thursday |  |  | Netezza TestMinor Refresh |  |  | Gap |  | SRDM REFRESH
| Matillion Compelte |  | Gap
Friday | SRDM REFRESH | [7 empty] | DEV IIT CLONING |  |  |  | Matillion Start (Monday)
[6 empty] | DataStage Exe. SR Request |  |  |  | DataStage RUN
| Data Not Synced |  |  | Monday | All day |  | Wednesday | In Sync after 5/6 pm |  | Friday | In Sync after 5/6pm
| Data In Sync |  |  | Tuesday | Not in Sync |  | Thursday | Not In sync
EST Time period for Netezza Testminor and Snowflake Testminor contain equivalent Data/is Synchronized