## Slide 1: IIT (A/B Testing) Release 1 – P1 Apps - Status as of 4/5
App | Scope | Job Execution Status |  | IIT Testing Status | IIT Execution Date | Plan Next Week (Current week?) | Overall Status
P1G1 | 5 Apps 51 jobs Vendor files: 9 | Data stage Sequence Executed : 5 Completed : 5 Failed : 0 | Matillion Sequence Executed : 5 Completed : 5 Failed : 0 | Apps Complete: 1/5 Total Test Cases : 72 Test Cases Executed : 63 Test Cases Passed: 61 Bugs raised :16 Bugs fixed : 13 | 04/01 - 4/12 | Complete A/B framework retesting | Progress : Test Case Execution %: 87
P1G2 | 4 Apps + 2 sub apps 79 jobs Vendor files : 60 | Data stage Sequence Executed : 12 Completed : 12 Failed : 0 | Matillion Sequence Executed : 12 Completed : 11 Failed : 1 | Apps Complete: 3/6 Total Test Cases : 480 Test Case Executed: 30 Test Cases Passed: 28 Bugs raised : 25 Bugs fixed : 23 | 3/18 - 3/15 3/22 4/4 4/26 | IIT Testing in Progress with exception of PDM | Blocked on PDM Progress : Test Case Execution %: 5
P1G3 | 7 Applications (+ 3 Sub-apps) 147 jobs Vendor files : 19 | Data stage Sequence Executed : 22 Completed : 22 Failed : 1 | Matillion Sequence Executed : 19 Completed : 18 Failed : 1 | Apps Complete: 0/10 Total Test Cases : 152 Test Case Executed: 35 Test Cases Passed: 33 Bugs raised : 25 Bugs fixed : 9 | 3/25 - 3/15 3/22 4/26 | IIT Test in Progress | Test Case Execution %:18
P1G4 | 2Applications 55 jobs Vendor files : 19 | Data stage Sequence Executed : 6 Completed : 2 Failed : 4 | Matillion Sequence Executed : 6 Completed : 1 Failed :5 | Apps Complete: 0/2 Total Test Cases : 152 Test Case Executed: 28 Test Cases Passed: 16 Bugs raised : 8 Bugs fixed : 1 | 4/2 – 4/26 | IIT Test in Progress | Test Case Execution :18% 4/6 app are failing DataStage Execution

## Slide 2: IIT (A/B Testing) Release 1 – MSS - Status as of 4/5
App | Scope | Job Execution Status |  | IIT Testing Status | IIT Execution Date | Plan Next Week (Current week?) | Overall Status
MSS Supply | 3Application 66 jobs Non Claims : 36 Claims : 218 263 Tables | Data stage Sequence Executed : 1 Completed : 1 Failed : | Matillion Sequence Executed : Completed : Failed : | Apps Complete: 0/3 Total Test Cases : 0 Test Case Executed:0 Test Cases Passed: 0 Bugs raised : 0 Bugs fixed : 0 | 3/25 – 4/5 4/1 – 5/10 | SQL Server cloning In Progress | 
MSS Demand | 17 Modules 204 jobs Files : 12 Table : 24 |  |  | Apps Complete: 0/1 | 3/18 - 5/3 3/18 – 4/23 4/19 – TBD |  |